## Slide 1
Quick Guide to the Transition Phase of the President’s Recovery Priorities
Ebola don go, leh we make Salone grow!
August – November 2017

## Slide 2: Contents
Background and overview of the President’s Recovery Priorities
Status of Initiatives to be tracked
Activity Planning
Delivery architecture –President’s Delivery Team, MDAs and Districts Structure
Community ownership and demand

## Slide 3: Background and context of the President’s Recovery Priorities
2015
2016
2017 and beyond
Timeline of the Sierra Leone Recovery and Agenda for Prosperity
Ebola Response
President’s Recovery Priorities (10-24 months)
Early Recovery (6-9 Months)
Agenda for Prosperity
National Recovery Strategy
Delivering outcomes whilst building capacity
24 months
Transition
Phase
(4 months)
4 months

## Slide 4: The President’s Recovery Priorities – 4 Months Transistioning Phase
05
34
07
08
18
Priority Sectors
Education, Energy, Health, Water, Finance
Priority Initiatives
Getting to 100% target completion of selected 10-24 months PRP initiatives, providing further support to selected infrastructure projects in the energy and water sectors and local govt. revenue
Sub-initiatives
Targeted for completion across 5 priority sectors across the country
Participating MDAs
Ministries of Education, Energy, Health, Water, Finance, Freetown City Council and Western Area Rural District Council (WARD C)
Key Result Areas
Enabling the achievement of over 50% of the 13 Key Result Area targets of the 12-24 months plus increasing local government revenue generation

## Slide 5: PRP Extension Initiatives
Initiatives
Strengthen national community health worker programme
Develop functional national ambulance service
Strengthen supply chain system
Improve community sanitation (Operation Clean Freetown)
Sector
Clear payroll and reallocate teachers
Reduce unapproved schools
Construct 500 furnished classrooms
School feeding programme
Rehabilitate existing Freetown water supply infrastructure and implement pro-poor water supply
Install electricity in schools, hospitals and other institutions and build solar systems (UNOPS)
Establish collection account and sector wide budget
T&D upgrades in Western Area and Wellington Express Line plus Kick-starting the CEC project
30 MW HFO IPP
30 MW HFO Government Owned
14-50 MW Grid Solar
Increase property tax base
Improve management of property tax with focus on tax efficiency, effectiveness and equity
Enhance revenue mobilization strategy

## Slide 6: The Transition Phase continues with …..
  Decentralisation: implementation and accountability continues at district, chiefdom and section levels and takes into account the de-amalgamation which created 41 new chiefdoms
  Concrete targets: targets are concrete, measurable and achievable
  Committed top leadership: His Excellency the President remains committed to driving delivery
  Transparency and accountability: clear and objective reporting of progress across all sectors
  Sustainable empowerment: transitioning of PDT process & systems across all levels of MDAs including Ministry of Local Government & Rural Development
Prioritisation: focus on 5 priority sectors
Robust performance management: weekly activity tracking, tracking progress against KPIs, District and Central sector meetings, and active problem-solving of issues as they arise continues

## Slide 7: Extension Initiatives: December 2017 forecast
60% of the Initiatives will meet 100% of their targets by Dec’17
100% of target met
0%-49% of target met
50%-99% of target met
Expected progress as at July ‘17
Chart: 
red | 4
amber | 8
green | 3
Breakdown of the 15 Initiatives RAG rating
Chart: 
red | 0
amber | 6
green | 9
20%
53%
27%
60%
40%
Expected progress as at Dec ‘17
Initiative
Sector
Health
Strengthen national community health worker programme
Develop functional national ambulance service
Improve community sanitation (Operation Clean Freetown)
Education
Clear payroll and reallocate teachers
Reduce unapproved schools
Construct 500 furnished classrooms (phase 2)
School feeding programme
Energy
Install electricity in hospitals and other institutions and build solar systems (UNOPS)
30 MW HFO (Government Owned)
Water
Rehabilitate existing Freetown water supply infrastructure and implement pro-poor water supply
Health
Strengthen supply chain system
Establish collection account and sector wide budget
30 MW HFO IPP
50 mw Solar IPP
128 MW Western Area Generation Project (CEC)
Energy
*Excluding Finance initiatives, forecast as at 26th September 2017

## Slide 8: Planning Timeline (MOHS, MEST, MOWR, GOV,MOE)
Aug
SEPT
13
27
10
24
Unlocked plans provided to sectors
Plan development
Extension Phase Activity Plan Timeline
IWGs (MOHS, MEST,MOWR, GOV) update existing activity plans
Adjusted milestones submitted to PDT for review
Tracking commences
Comments provided to sectors (from PDT & Districts)
Final drafts submitted by sectors
Plans locked
District and CDT review of plans
Final review (with amendment, as necessary)
Mon, 21st
Mon, 14th
Fri, 1st
Mon, 28th
Thurs, 7th
20
3
17
Tues, 22nd
Fri, 8th
Tues, 12th

## Slide 9: Delivery Structure of the Transition President's Delivery Team
Plan, oversee, and report to Presidential and Ministerial Delivery Forum
Districts implement and report to Central MDAs
Monitor and evaluate
Core responsibility
** Reduced Direct support personnel from
  Central MDAs
  Ministers, Commissioners
  KRA Leads, Initiative and sub-initiative owners
  Sector Transition Facilitators
  District MDAs
  District Councils for devolved functions
  District-based implementing partners
  Private Sector participants
  District Transition Facilitators
  Central and District MDAs
  Paramount Chiefs
  District Councils
Presidential Delivery Team
  Central Delivery
  Team support
  all functions
Community ownership is critical to success

## Slide 10: Delivery structures within the MDAs
Minister
KRA 1 Lead
KRA 2 Lead
TF
MDA Delivery Team Composition:
Minister (or designate)
KRA Leads
Priority Initiative Owners
M&E Officer
Comms Officer / PRO
Sector Transition Facilitator
TF
Transition Facilitator (SF)
Works directly with MDA leadership, including Minister, to drive delivery
Supports MDA KRA Lead(s) and works with the Priority Initiative Owners
Initiative Working Group Composition:
Priority Initiative Owner (internal to MDA)
Sub-initiative owners from responsible MDAs
Other technical support, as needed
Implementing partner(s)
Relevant development partner(s)
Other stakeholders
Sector Transition Facilitator
Priority initiative working groups:

## Slide 11: Delivery structures at District Level
District Delivery Forum
District Sector Meeting
District Delivery Forum:
Council Chairman (co-chaired by Mayor, where applicable)
Chief Administrator
Heads of District MDAs
District Transition Facilitator
DTF
District Transition Facilitator
Supports District Council in its coordination and oversight role
Supports District Council and MDAs for monitoring & evaluation and data analysis related to the PRPs
Works with District Office and Paramount Chiefs to support community-level engagement
District Sector Meeting Composition:
Head of District MDA
M&E Officer
Sector representative from District Council
Implementing Partners
District Transition Facilitator
District Sector Meeting
District Sector Meeting
DTF

## Slide 12: Bi-Weekly - Implementation of initiatives tracked for completion, performance and accountability
Priority initiatives and sub-initiatives show weekly progress through trackers reported at Presidential and Ministerial Delivery Forums
Each priority initiative and sub-initiative team have selected performance metrics…
Key Performance Indicators (KPIs) and Delivery Indicators (DIs) monitor success at the KRA through sub-initiative levels
… which are reported on regularly to track progress
Implementation of detailed activity plans updated in Activity Tracker on a bi-weekly basis

## Slide 13: Bi-Weekly implementation rhythm designed to report progress and to identify, escalate and resolve issues
Presidential/ Ministerial Delivery Forum Thurs, 2pm
MDA Initiative Working Groups & District Sector Meetings Bi-Weekly sessions held before & after Activity Tracker submission
  PDT aggregates MDA submissions to collate Milestones hit/missed and create Delivery Forum outputs (e.g. milestone summary and issues for resolution)
Additional
mechanisms for issues identification and resolution:
  Daily District sector specific issues log
  Fortnightly Sector Deep Dives to review milestones missed
  Post Delivery Forum, Sector Action Trackers produced and follow-up happens via:
    HE meetings
    Bi-lateral MDA meetings
    Other actions
  MDAs:
    Implement activities at District and Central level, directly or via Implementing Partners
    Update activity trackers to report implementation
    Resolve/escalate issues affecting implementation
Activity tracker updates submitted by MDAs bi-weekly on Tues, 5pm
  Bi-Weekly
  implementation
  rhythm

## Slide 14
Chiefdom and section-level monitoring during transition phase impacted by creation of 41 new chiefdoms
Transition Phase Section Targets ( to be updated)
Chart: Breakdown of Sections by Number of Relevant Delivery Indicators
| Section TBD | 1 | 2-3 | 4-10 | >10
Number of sections | 611 | 846 | 463 | 225 | 44
Energy: 1
Education: 2
Health: 3
Delivery Indicators to be made available at Section-level
Additional 41 newly created chiefdoms increases monitoring from 149 to 190 chiefdoms
*As at September 72% of sections had 2 or more indicators to monitor

## Slide 15: District Breakdown of Extension Initiatives to be tracked

## Slide 16: Communication Strategy: We are using online, social and traditional media to keep citizens and stakeholders informed
195,000 reached through WhatsApp This Week in Recovery
239,000 reached through Facebook
>700
Twitter followers
Regular articles in the printed press
presidentsrecoverypriorities.gov.sl
Dedicated PRP website
“…the presence of a delivery unit is not the only way to drive delivery and demonstrate leadership commitment…citizen feedback is widely used in many countries. In fact, the wide use of social media and technology has further amplified the pressure for political leaders and governments to deliver”
“Ministers share experience of leadership for delivery” - World Bank Feature Article June 2014
News and updates on the PRP across various radio stations

## Slide 17: The PRP monitoring mechanisms to ensure effective implementation of the PRPs
External monitoring mechanisms
  SABI consortium
  Independent evaluators
GoSL monitoring mechanisms
  PDT
  MDAs
  District Councils
  Paramount / Section Chiefs